## Sheet1
|  | Index: | A+ Pruning Recommendation | In Process | Completed | Bomb Cyclone Insurance? | Partial
Priority | PROBLEM | Date Entered | LOCATION | ACTION | Provider/Fixer | Status | Date Completed | Comments | PHOTOS | PHOTOS | PHOTOS
| Holly Tree Overgrown and getting close to power lines |  | East side of Building A | Prune Holly Tree |  |  |  | May be call PSE to trim it ? | 2025 NOV 03 A
| Overhanging Tree Limbs |  | Maple at NE corner of F, Maple at NE corner of A. See A+ arborist's sightings | Prune trees to allow 8' clearance above ground and any trees touching roofs. |  |  |  |  | No Photo at this time
| Dying Plants |  | Surrounding North Garbage Corral | prune or remove |  |  |  |  | 2025 NOV 03 B
| Log debris |  | North of Wetland along Juniper | Navneet has offered his chainsaw to cut up limbs, but is unable to assist personally. (Boy Scouts solution was not viable due to privately owned land.) |  |  |  | Solution Pending | 2025 NOV 03 D | 2025 NOV 03 D1
| Sidewalk Missing |  | North side of property between wetland & townhouse | contact owner of townhouse (Bill Vipond?) to see if they are still able to reinstate the sidewalk from our North parking to sidwalk along Juniper. |  |  |  |  | Sidewalk is missing so no photo
| Crowded & Possibly Unhealthy Plants |  | NW corner of building B | prune or remove |  |  |  | SBD suggests Pruning is best done in spring | 2025 NOV 03 E
| Crack in siding |  | Building B North of 101 | Fix (caulk?) siding. Can our monthly repair person fix this? |  |  |  | Put in request to Rachel 10/29/25 | 2025 NOV 03 G
| Wetland Maintenance. We are required by the city to maintain a natural habitat but have no guidance on how to do so. We are then left with costly drainage issues, overgrowth, & treefall with no support from the city. |  | NW section of property is a wetland (Note topped pine in the background. Possible water damage & decay may begin and weaken the tree.) | Reach out to city for help. Budget line item to support property owners who need help maintaining this water filtration system? Can we sell the land back to them so they can maintain it properly? |  |  |  |  | 2025 NOV 03 H | 2025 NOV 03 H1
| Maple branches too low & touching roof of structures |  | Maple at NE corner of F, Maple at NE corner of A have branches lower than 8'. Maple building B & C are close to touching roof and carport in front of C. | Prune Maples. See A+ arborist's sightings |  |  |  |  | 2025 NOV 03 I | 2025 NOV 03 I1
| Damaged Shrub due to oak tree damage from bomb cyclone |  | East side of building C between 102-103 | Suggestion: Remove any dead part of destrooyed plant and restore with new shrub. Check with owners to see if they would prefer a lower hedge bush. |  |  |  |  | 2025 NOV 03 J
| Sinkhole |  | East side of building C between 102-103 | Landscapers had filled this in before, but sinkhole continues to sink. Possibly underground stream? Research best solution |  |  |  |  | 2025 NOV 03 K
| Rusted Bannister |  | F201 entrance railing | Check for safety, repair or replace. |  |  |  |  | 2025 NOV 03 L | 2025 NOV 03 L1
| Debris: bench, coil springs, wood, pallet, microwave, compost bin |  | Debris is scattered around the garbage corral and behind the shed between buildings D & C | Dispose of: sofa, coil springs, palet, compost bin, metal structural supports |  | Partial |  | Photos 10/3/25 | 2025 NOV 03 M | 2025 NOV 03 M1
| Dry & Disheveled plants & Bomb Cyclone tree trunk logs |  | SW corner of C building garden | Keep groundcover, prune rhodie, mulch bed, remove or reuse 3 logs |  |  |  |  | 2025 NOV 03 N
| Fern blocking vent |  | South side of F102 | Remove fern and replant a few feet over. |  |  |  |  | 2025 NOV 03 O
| Dead grass, overgrown moss, Broken Sprinklers |  | Buildings D & F south sides, E South & SE sides. | Obtain estimate from Southern By Design for repair. Present pros-cons to board |  | Estimation |  |  | No photo needed
| Irrigation |  | Center Courtyard, West Side (along redwood fence with new plants) . Check to see if NE area across from Bldg A has irrigation. New plants will be added in fall or spring. | Obtain estimate from Southern By Design for repair & inquire best time to repair |  | Estimation |  |  | No Photo needed
3 | Dirty Privacy Fences |  | Most fences are dirty | Will powerwashing take off paint? This could possibly be a job for our monthly maintenance person. |  |  |  |  | Fences are in different stages of dirty
3 | Tresspassing & Dog Use by non-residents |  | SE corner of property at 5th Ave NW & Holly | Possible solutions: No trespassing sign or Pick Up After Your Dog sign. Perhaps planting boxwood or another plant along this are may deter animal walkers. |  |  |  |  | 2025 NOV 03 P
| Dying Tree |  | South side of Building E 102. Tree is rotting with root ball lifting out of ground forcing limbs to lean | Pruning has already happened removing the rotted limbs. Community Volunteers are able to remove tree, if advised. Owners of E102 & E202 have been notified and are willing to have it be removed. |  |  |  |  | 2025 NOV 03 Q
| Dry Earth & No ground cover (grass)! |  | South of E104 & F 101-102 | Resoil and weed. |  |  |  |  | 2025 NOV 03 R
| Siding Damage |  | SE corner of Building D | Repair siding and flashing which may include rodent-proof meshing. Can our monthly repair person fix this? |  |  |  | Put in request to Rachel 11/6/25 | 2025 NOV 03 S
| Rhododenron in Trouble |  | Squeezed inbetween Barberry Bushes | Perhaps move Rhodie to where it can thrive |  |  |  |  | 2025 NOV 03 T
| Dying Tree |  | South side of Building F (the one which had a rotting limb that was recently removed | Check A-Plus Estimate #20 may be this tree. Check with arborist if pruning will save it, but one large limb has already been removed due to rot. |  |  |  |  | 2025 NOV 03 C
| Overgrown Douglas Fir trees |  | SE Corner pines are low and touching building E | Pruning. A-Plus Estimate has this as #5 |  |  |  |  | 2025 NOV 03 U
| Two Maples 1-touching roof, 2-unhealthy |  | SW corner of Buildng E | A-Plus Estimate has Maple touching roof as #3. Smaller maple may be #4 recommending pruning. |  |  |  |  | 2025 NOV 03 V | 2025 NOV 03 V1
| crawlspace vents blocked |  | West side of Building F |  | Greg (Community Gardener) will fix/clear | In Process |  |  | 2025 NOV 03 F
| Ivy & Holly Invasive Plants |  | East side of Building A & B as well as SE entrance plant mount. Holly is invading all areas of the property. | Southern By Design has been notifed to instruct workers to remove invasive ivy from siding and ground. |  |  |  |  | 2025 NOV 03 W | 2025 NOV 03 W1
| Dying Plants |  | North side of Building C Rhodie | Prune or remove or replant | Southern by Design |  |  | Southern By Design has been notified and will remove or replant | 2025 NOV 03 X | 2025 NOV 03X1
| Stunted Plant |  | NW corner of small island of land near Building B | Give it time to recover. | Nature |  |  | SBD has recommended giving it time to recover. | 2025 NOV 03 Y
| crawlspace vents blocked |  | East side Building B | create space and remove vines to allow for air flow |  |  |  | SBC will remove plantlife from vents | 2025 NOV 03 Z
| Uprooted Rhododendron & wooden debris |  | North side of building C | Remove wooden debris from roof repair. Wesley from Southern By Design has noted this. |  |  |  | In Process | 2025 NOV 03 AA | 2025 NOV 03 AA1
| Possible improper pruning of Particular Bush |  | What we think are Japanse Barberry Bushes are scattered througout our property, but they are being pruned to look like a deranged light bulb (photo on Left) instead of what it wants to be - a Shining Star (Stock photo on Right) | Shared our pruning preference with Southern by Design. They will only prune once/year and allow plant to thrive. |  |  |  | Southern By Design has been notified and will only trim once a year. | 2025 NOV 03 BB | 2025 NOV 03 BB1
| Fence Surrounding Wetland Broken |  | Wooden fence surrounding wetland in NW corner of property | Will INSURANCE will cover this repair? Check with city to see if it is necessary to replace. Contact at city may be Evan Brumfield, Environmental Science Assistant, evanb@issaquahwa.gov |  |  |  | Insurance Adjustor recommended this repair be covered. | 2025 NOV 03 CC
| Bomb Cyclone tree trunk logs |  | Southern walkway of building C | Find a reuse for the left over tree trunks logs: planters? Firewood? Seats? They need to be moved for safety as they're on the sidewalk. Find owner of petunia plant beautification and ask what they'd like to do with them. |  |  |  | removed Saturday 11/1 by friends of Bobbi's | 2025 NOV 03 DD
| Tall Grass |  | NW grass strip between walkway and wetland | clear sticks & debris |  |  |  | 9/13-Debris has been removed and grass has been cut | 2025 NOV 03 EE
| Falling Fence |  | NE corner of property surrounding the abandoned house on the corner. | Contact city reporting code violation after the 5 stumps are removed on 9/8/25. Owner cleared fallen fence & tidied land. Partial falling fence remains. |  |  |  | October 2025 debris removed. One portion of falling fence still remains | 2025 NOV 03 FF
| Broken Firelane Curbs caused by Trees Uprooted by Bomb Cyclone |  | West side of property along buildings B & C | McBride is taking care of this. |  |  |  | Completed September 2025 | 2025 NOV 03 GG | 2025 NOV 03 GG1
| Dead or Dying Plant |  | NE corner of C101 Patio | prune or remove |  |  |  | Completed Landscaper removed dead plant | 2025 NOV 03 HH
| Screens removed and laying outside of unit |  | D 102 | Can EMB please Request that renters/owners put them back. |  |  |  | 9/22 Notified Rachel | 2025 NOV 02 II
| Overhanging air conditioner and wooden fill. |  | West window D102 | Request that renters remove illegal air conditioner and resotre window as original Refernce IV section D. |  |  |  | 9/22 Notified Rachel | 2025 NOV 03 JJ
| Charcoal Grill |  | SW of D102 | Remind renters that outdoor grills are not allowed in common spaces. Reference to IV section D. |  |  |  | 9/22 Notified Rachel | 2025 NOV 03 KK
Note on A2: Microsoft Office User:

## Color Code
A+ Pruning Recommendation
In Process
Completed
Bomb Cyclone Insurance?